## Evaluation Report
Performance Evaluation Report
West Coast District Municipality
Output as per support plan | Output achieved | Allocation as per Support Plan | Allocation spent to date | Allocation still to be spent | Reasons for non achievement of output | Remedial Measures to be implemented | Date when output will be achieved
5 Interns Appointed | Yes | 500000 | 291739 | 208261 |  |  | 30/06/2016
Maintenance of Financial Systems | Yes | 750000 | 260273 | 489727 | Annual asset verification process will start in March 2016 | SCM process starts in February 2016 | 30/06/2016
|  |  |  | 0 |  |  | 30/06/2016
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Signature | Date
Municipal Manager
Chief Financial Officer
Note on A3: Select a Quarter from drop down list

## Cash Flow Projection
West Coast District Municipality Cash Flow Projection
|  | Quarter 1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Output as per support plan | Allocation still to be spent | July | August | September | October | November | December | January | February | March | April | May | June | Balance Outstanding
5 Interns Appointed | 208261 | Quarter 1 July: 41672; Quarter 1 August: 43756; Quarter 1 September: 44906; Q2 October: 45028; Q2 November: 90856; Q2 December: 21127 | -79084
Maintenance of Financial Systems | 489727 | Quarter 1 July: 0; Quarter 1 August: 0; Quarter 1 September: 98914; Q2 October: 157489; Q2 November: 8264 | 225060
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
| Signature | Quarter 1 July: Date
Municipal Manager
Chief Financial Officer