## Evaluation Report
Performance Evaluation Report
West Coast District Municipality
Output as per support plan | Output achieved | Allocation as per Support Plan | Allocation spent to date | Allocation still to be spent | Reasons for non achievement of output | Remedial Measures to be implemented | Date when output will be achieved
5 Interns Appointed | Yes | 500000 | 347370.3 | 152629.7 |  |  | 30/06/2015
Maintenance of Financial Systems | Yes | 675000 | 250572.57 | 424427.43 | Annual asset verification process will start in March 2015 | SCM process starts in February 2015 | 30/06/2015
Support the training of municipal officials on minimum competencies | Yes | 75000 | 0 | 75000 |  |  | 30/06/2015
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Signature | Date
Municipal Manager
Chief Financial Officer
Note on A3: Select a Quarter from drop down list

## Cash Flow Projection
West Coast District Municipality Cash Flow Projection
|  | Quarter 1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Output as per support plan | Allocation still to be spent | July | August | September | October | November | December | January | February | March | April | May | June | Balance Outstanding
5 Interns Appointed | 152629.7 | 26798.1 | 26798.1 | 42798.1 | 42782 | 55311 | 33670 | 33671 | 42471 | 43071 |  |  |  | -194740.6
Maintenance of Financial Systems | 424427.43 | 2074.94 | 98107.02 | 79939.61 | 40180 | 5784 | 4308 | 2616 | 5208 | 12355 |  |  |  | 173854.86
Support the training of municipal officials on minimum competencies | 75000 | [12 empty] | 75000
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
| Signature | Quarter 1 July: Date
Municipal Manager
Chief Financial Officer