## Evaluation Report
Performance Evaluation Report
West Coast District Municipality
Output as per support plan | Output achieved | Allocation as per Support Plan | Allocation spent to date | Allocation still to be spent | Reasons for non achievement of output | Remedial Measures to be implemented | Date when output will be achieved
5 Interns Appointed | Yes | 500000 | 290239 | 209761 |  |  | 30/06/2018
Maintenance of Financial Systems (MSCOA) | Yes | 750000 | 227450 | 522550 |  |  | 30/06/2018
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Signature | Date
Municipal Manager
Chief Financial Officer
Note on A3: Select a Quarter from drop down list

## Cash Flow Projection
West Coast District Municipality Cash Flow Projection
|  | Quarter 1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Output as per support plan | Allocation still to be spent | July | August | September | October | November | December | January | February | March | April | May | June | Balance Outstanding
5 Interns Appointed | 209761 | Quarter 1 July: 43278; Quarter 1 August: 35270; Quarter 1 September: 46500; Q2 October: 70233; Q2 November: 64549; Q2 December: 30409 | -80478
Maintenance of Financial Systems (MSCOA) | 522550 | Quarter 1 July: 61660; Quarter 1 August: 0; Quarter 1 September: 0; Q2 October: 0; Q2 November: 165445; Q2 December: 345 | 295100
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
| Signature | Quarter 1 July: Date
Municipal Manager
Chief Financial Officer