## WC DM
NAME OF THE MUNICIPALITY: West Coast District Municipality
Top 10 Projects: 1 major project per vote
| Name of the Project | Budgeted amount for 2017/18 (R'000) | New/Roll-over project | Roll-over project (R'000) |  |  | Quarter 2 |  |  |  | Brief process plan for Q1 ending on 30 September 2016 | Foreseeable challenges on implementation of the project | Projected completion date
|  |  |  | Amount and initiation year | Actual expenditure as at 31 December 2017 | % of budget spent | SDBIP YTD Projections (R'000) | YTD Actual expenditure (R'000) | Commitments (new and roll-over projects) (R'000) | % Difference of YTD SDBIP and Actual Expenditure
1 | Call Taking & Dispatch Sistem | 300000 |  | 300000 | 0 |  | 206100 | 0 |  | 0 |  | no | 30/06/2018
2 | Build Tank & Equipment | 537800 |  | 537800 | 171165 | 31.8269 | 369468.6 | 171165 |  | 46.3273 |  | no | 30/06/2018
3 | Radio Equipment / Infrastructure | 330000 |  | 330000 | 12800 |  | 226710 | 12800 |  | 5.646 |  | no | 30/06/2018
4 | Firetruck | 1450000 |  | 1450000 | 0 | 0 | 996150 | 0 |  | 0 |  | no | 30/06/2018
5 | Vehicles | 750000 |  | 750000 | 0 |  | 515250 | 0 |  | 0 |  | no | 30/06/2018
6 | Flow Meters & Instrumentasie | 250000 |  | 250000 | 55830 | 22.332 | 171750 | 55830 |  | 32.5066 |  | no | 30/06/2018
9 | Valves | 1350000 |  | 1350000 | 136462 |  | 927450 | 136462 |  | 14.7137 |  | no | 30/06/2018
10 | Pipe replacement | 1600000 |  | 1600000 | 114946 | 7.1841 | 1099200 | 114946 |  | 10.4572 |  | no | 30/06/2018
Note on L7: Elizabeth de Lange: What is the progress for projects to date.
Note on L9: Elizabeth de Lange: What is the progress for projects to date.
Note on L11: Elizabeth de Lange: What is the progress for projects to date.
Note on M6: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on M7: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on M8: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on M9: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on M10: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on M11: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on M12: Elizabeth de Lange: Is there any challenges if not then indicate so.