## WC DM
NAME OF THE MUNICIPALITY: West Coast District Municipality
Top 5 Projects: 1 major project per vote
Name of the Project | Budgeted amount for 2016/17 (R'000) | New/Roll-over project | Roll-over project (R'000) |  |  | Quarter 4 |  |  |  | Brief process plan for Q1 ending on 30 September 2016 | Foreseeable challenges on implementation of the project | Projected completion date
|  |  | Amount and initiation year | Actual expenditure as at 31 December 2016 | % of budget spent | SDBIP YTD Projections (R'000) | YTD Actual expenditure (R'000) | Commitments (new and roll-over projects) (R'000) | % Difference of YTD SDBIP and Actual Expenditure
1. Water | [9 empty] | completed | no
1.1) Water : Misverstand WTW | 250000 |  | 250000 | 0 | 0 | 250000 | 0 |  | 0 |  |  | 30/06/2017
[10 empty] | completed | no
1.2) Water : Voelvlei Housing ( Reservoir / pipeline ) | 500000 |  | 500000 | 0 | 0 | 500000 | 0 |  | 0 |  |  | 30/06/2017
[10 empty] | completed | no
1.3) Water : Pipe Replacement | 2650000 |  | 2650000 | 362291 | 13.6714 | 2650000 | 362291 |  | 13.6714 |  |  | 30/06/2017
[10 empty] | completed | no
1.4) Water : Pipe Valves | 2150000 |  | 2150000 | 111272 | 5.1754 | 2150000 | 111272 |  | 5.1754 |  |  | 30/06/2017
Note on K5: Elizabeth de Lange: What is the progress for projects to date.
Note on K7: Elizabeth de Lange: What is the progress for projects to date.
Note on K9: Elizabeth de Lange: What is the progress for projects to date.
Note on K11: Elizabeth de Lange: What is the progress for projects to date.
Note on L5: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on L7: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on L9: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on L11: Elizabeth de Lange: Is there any challenges if not then indicate so.
Note on M5: Elizabeth de Lange: When will the project be completed.
Note on M7: Elizabeth de Lange: When will the project be completed.
Note on M9: Elizabeth de Lange: When will the project be completed.
Note on M11: Elizabeth de Lange: When will the project be completed.